## Sprint1
Calendar days | Planned | Actual
1st February | 4 | 4
2nd February | 4 | 4
3rd February | 4 | 4
4th February | 4 | 3
5th February | 4 | 3
6th February | 3 | 3
7th February | 3 | 3
8th February | 3 | 3
9th February | 3 | 3
10th February | 2 | 3
11th February | 2 | 2
12th February | 2 | 1
13th February | 1 | 1
14th February | 0 | 0
15th February | 0 | 0

## Sprint2
Calendar days | Planned | Actual
16th February | 3 | 3
17th February | 3 | 3
18th February | 3 | 3
19th February | 3 | 2
20th February | 3 | 2
21st February | 2 | 2
22nd February | 2 | 2
23rd February | 2 | 2
24th February | 2 | 1
25th February | 1 | 1
26th February | 1 | 0
27th February | 1 | 0
28th February | 0 | 0
29th February | 0 | 0

## Sprint3
Calendar days | Planned | Actual
1st March | 5 | 5
2nd March | 5 | 5
3rd March | 5 | 5
4th March | 4 | 5
5th March | 4 | 4
6th March | 3 | 4
7th March | 3 | 4
8th March | 3 | 4
9th March | 2 | 3
10th March | 2 | 3
11th March | 2 | 2
12th March | 1 | 2
13th March | 1 | 1
14th March | 1 | 1
15th March | 0 | 0

## Sprint4
Calendar days | Planned | Actual
16th March | 5 | 5
17th March | 5 | 5
18th March | 5 | 4
19th March | 4 | 4
20th March | 4 | 3
21st March | 4 | 3
22nd March | 4 | 3
23rd March | 3 | 3
24th March | 3 | 2
25th March | 2 | 1
26th March | 2 | 1
27th March | 1 | 1
28th March | 1 | 0
29th March | 1 | 0
30th March | 0 | 0

## Sprint5
Calendar days | Planned | Actual
1st April | 4 | 4
2nd April | 4 | 4
3rd April | 3 | 3
4th April | 3 | 3
5th April | 3 | 3
6th April | 3 | 3
7th April | 3 | 2
8th April | 2 | 2
9th April | 2 | 1
10th April | 1 | 1
11th April | 1 | 1
12th April | 1 | 1
13th April | 1 | 1
14th April | 1 | 0
15th April | 0 | 0

## Sprint6
Calendar days | Planned | Actual
16th April | 3 | 3
17th April | 3 | 3
18th April | 3 | 3
19th April | 3 | 3
20th April | 3 | 2
21st April | 2 | 2
22nd April | 2 | 2
23rd April | 2 | 1
24th April | 1 | 1
25th April | 1 | 1
26th April | 1 | 1
27th April | 1 | 1
28th April | 1 | 0
29 April | 1 | 0
30 April | 0 | 0