## Sprint1
Calendar days | Planned | Actual
1st February | 4 | 4
2nd February | 4 | 4
3rd February | 4 | 4
4th February | 4 | 3
5th February | 4 | 3
6th February | 3 | 3
7th February | 3 | 3
8th February | 3 | 3
9th February | 3 | 3
10th February | 2 | 3
11th February | 2 | 2
12th February | 2 | 1
13th February | 1 | 1
14th February | 0 | 0
15th February | 0 | 0

## Sprint2
Calendar days | Planned | Actual
16 th February | 3 | 3
17 th February | 3 | 3
18 th February | 3 | 3
19 th February | 3 | 2
20 th February | 3 | 2
21 st February | 2 | 2
22 nd February | 2 | 2
23 rd February | 2 | 2
24 th February | 2 | 1
25 th February | 1 | 1
26 th February | 1 | 0
27 th February | 1 | 0
28 th February | 0 | 0
29 th February | 0 | 0
1 st March | 0 | 0